## Slide 1: Steering Committee
October 1, 2025

## Slide 2: Agenda
2025-26 progress report.
Significant TMG-supported projects.
Potential New Members.
Preliminary look-ahead to 2026-27.
Draft 2026-27 budget.
Other Business.
Adjournment.

## Slide 3: 2025-26 Work Plan

## Slide 4: TTS 2022 Analysis (1)
First round of analysis is complete. Available on the TMG website:
  CTRF presentation:
  Gao, Y., Y. Liu and E.J. Miller, “Pre/Post Pandemic Travel Behaviour in the Greater Golden Horseshoe”, presented at the 60th Annual Conference of the Canadian Transportation Research Forum, Ottawa: May 25-28, 2025.
  TMG technical report:
  Gao, Y., Y. Lin and E.J. Miller, Changing Travel Behaviour in the GGH: Analysis of TTS 2022, Toronto: Travel Modelling Group, University of Toronto, June 10, 2025, 74 pages.
Continuing to look at WaH/WfH using TTS and THATS data, including some exploratory modelling.

## Slide 5: TTS 2022 Analysis (2): A Few Findings
As expected, instrument bias & non-respondent bias are detected & will need adjusting for when modelling trip/activity generation (at a minimum).
Despite weightings, concerns about sample bias exist.
  Need to compare to census data.
Difficult to differentiate between possible survey biases & actual changes from 2016.
Transit under-count is a serious concern.
WaH/WfH effects are quite evident.
  Largely appear to be as expected.
  Affects overall daily activity patterns, not just commuting (more below).
Some indications of 2022-23 changes. Will continue to investigate.

## Slide 6: TTS 2022 Analysis (3): Modelling Implications
Re-weighting is a possibility, but has issues as well:
  Multiple versions of TTS.
  Re-weighting is a challenging task.
Less reliance on TTS for model development:
  Census data for population & employment synthesis.
  More extensive use of road & transit count data for calibration.
In V4.3 we will investigate a multi-year estimation process (at a minimum 2016 + 2022/23).

## Slide 7: GTAModel V4.3 (1)
Much preliminary work has been undertaken:
  2022 GGH network developed.
  Numerous model-specific studies (next slides).
Expecting V4.3 still to be completed this (2025-26) work year; hopefully by end of 2025.
  Tie in to Durham model update, among others.
Working on V5.0 design, but this will largely be work for 2026.

## Slide 8: V4.3 Projects Underway (2)
Volume-delay function investigation:
  Collaborating with Metrolinx.
  Summer student (Justin Fang) working with Henry; collaborated with Metrolinx.
  Work on this will continue.
Vehicle-for-hire modelling:
  Collaborating with Toronto Transportation Services.
  “Auto passenger” modelling.
  Continuing development of PTC simulation model in GTAModel.
  One each of postdoc, PhD student, MEng student & undergrad working with TMG staff.
Bicycle route choice modelling.
  Continuing to develop a bicycle route choice model.
  Collaborating with Profs. Saxe & Chan.
  Postdoc working with TMG staff.
Transit reliability modelling in Emme.
  Collaborating with Prof. Shalaby & Visiting Prof. Babazadeh
  Two postdocs working on this.

## Slide 9: Modelling Auto Passenger Modes (work led by Dr. Ya Gao)
Transit access/egress by PTC (Colin Ye).
Carpools (Coco Lam).
Serve dependents (Usman Ahmed).
Auto
(drive)
Public Transit
WAT
DAT
PAT/PET
“Auto-Based
Passenger”
Intra-household:
Passenger
Rideshare
Inter/non-household:
Carpool
PTC
Taxi
Active Modes
Bicycle
Walk-all-way
MODE CHOICE

## Slide 10: Parking (Residential & Non-Home Destinations)
PhD student Ladan Berahman is nearing completion of her PhD thesis (Supported by MEng student Trevor Jones).
Will provide input to V4.3/V5.0 upgrades.
Papers / presentations:
Berahman, L., M. Haghighi and E.J. Miller (2025) “Comparing Tour-Based and Trip-Based Mode Choice Models: A Focus on Residential Parking Impacts” submitted to Transportation Letters.
Jones, T. L. Berahman and E.J. Miller (2025) “Analyzing the relationship between on-street parking demand and illegal parking”, to be presented at the 2025 Transportation Association of Canada Annual Conference, Quebec City, October, 5-8.
Berahman, L, M. Haghighi and E.J. Miller (2025) “Trip-Based Mode Choice Model: A Focus on Residential Parking Impacts”, presented at the 60th Annual Conference of the Canadian Transportation Research Forum, Ottawa: May 25-28.
Jones, T., L. Berahman and E.J. Miller (2025) “The Lasting Impact of the COVID-19 Pandemic on Urban Transportation Systems: A Case Study of On-Street Parking in Toronto”, presented at the 60th Annual Conference of the Canadian Transportation Research Forum, Ottawa: May 25-28.
Jones, T., L. Berahman and E.J. Miller (2025) “Analyzing the Relationship Between On-Street Parking and Land-Use”, presented at the 60th Annual Conference of the Canadian Transportation Research Forum, Ottawa: May 25-28.
Berahman, L. and E.J. Miller (2025) “Measuring the Impact of Residential Parking on Car Ownership Levels”, presented at the 104th Annual Meeting of the TRB, January 5-9.
Berahman, L., M. Haghighi and E.J. Miller, (2024)“Investigating the Impact of Residential Parking Types on Activity Scheduling”, presented at the Canadian Transportation Research Forum 59th Annual Conference, Kelowna, BC, May 12-15.

## Slide 11: Auto Ownership & Other Mobility Tools
PhD thesis underway by Mwendwa Kiko.
Will provide input to V4.3/V5.0 upgrades.
Papers / presentations:
Kiko. M., J. Zhang, Y. Zhang and E.J. Miller (2026) “From Coast to Coast: Understanding and Predicting BEV Adoption Across Canadian Regions”, submitted for presentation at the WCTR 2026 conference, Toulouse, France, July 6-10.
Kiko, M. and E.J. Miller (2025) “Factors Influencing Car Ownership in Toronto: Insights from a Hurdle-Ordered Model”, submitted to International Journal of Sustainable Transportation.
Kiko, M. and E.J. Miller (2024) “Jointly Modelling Car and Transit Pass Ownership in Toronto in 2011 and 2016”, submitted to Travel Behaviour & Society.
Kiko, M. and E.J. Miller (2024) “EVs and Gas Stations: Insights from a Travel Demand Model”, presented at the CATTS/TAL Symposium, Toronto: November 5.
Kiko, M. and E.J. Miller (2024) “The Interaction of Short-run Travel Behaviour and Long-run Vehicle Ownership: A Study using Ordered Models of Vehicle Ownership Level”, presented at the 17th International Conference on Travel Behaviour Research, Vienna, July 14-18.

## Slide 12: Work at Home (WaH) & Work from Home (WfH)
We are continuing to investigate WaH & WfH processes using both TTS and THATS data*.
Papers & presentations dealing with this topic in various ways:
Haghighi, M., L. Berahman and E.J. Miller (2025) “The Post-Pandemic Hybrid Work Environment and Its Impacts on Weekly Trip-Making Behaviour”, presented at the 60th Annual Conference of the Canadian Transportation Research Forum, Ottawa: May 25-28.
Dong, Z. and E.J. Miller (2024) “Out-of-home non-work/school activity participation in a flexible work future: A comparative study between pre- and post-pandemic eras among remote, on-site, and hybrid workers” submitted to Transportation.
* Haghighi, M. and E.J. Miller (2024) “Week-Long Activity-Trip Diary Data Collection Using a Smartphone Application: Design, Implementation & Results of the ‘THATS’ Survey”, submitted to Transportation.
* Haghighi, M. and E.J. Miller (2023) A Comprehensive Report of the Design and Implementation of THATS Survey. University of Toronto, July. https://tmg.utoronto.ca/wp-content/uploads/2023/08/THATS-Design-Comprehensive-Report-August2_compressed.pdf

## Slide 13: V4.3 (3): Other Related Student Projects
GO Bus modelling (Grace Zhang).
ILUTE/2 (Charlie Martinez, Billie Zhang, Jason Zhang, Nora Liu)
Use of GTAModel to analyse GO expansion benefits (Richard Lee).
A number of student- & postdoc-based projects are underway in support of GTAModel V4.3 / V5.0:

## Slide 14: On-going Maintenance & Support
As always, considerable staff time is expended supporting members’ use of TMG software & networks.
Continuing to support PopSyn3 applications.
  Would very much like to get agencies off PopSyn3 and using more “modern” procedures. This should be a priority as agencies undertake model system updates.
Support for agencies’ consultants use of GTAModel.
  CIMA+, HDR, …
XTMF updates.
Documentation.

## Slide 15: XTMF Updates
Added globalization support for XTMF GUI, now available in French and Spanish:
  Translations need testing from native speakers still.
  Does not include translations for run logs or run errors yet.
Automated Calibration Framework.
  Over the past year we have developed a customizable automated calibration framework within XTMF.
    Dramatically speeds up and systematizes calibration.
  New target type - Probability Vector Target.
    Useful for calibrating auto ownership and driver license models.
  New module to extract driver license rates by home zone for customizable demographic segments

## Slide 16: Documentation
Slides from an all-day workshop given at UNSW, Sydney, Australia on Sept. 2/25 can be found at:
https://tmg.utoronto.ca/wp-content/uploads/2025/09/ABM-Workshop_EJMiller_UNSW_Sept-02-25.pdf
Also, of course, current documentation can be found at:
https://tmg.utoronto.ca/doc/1.6/gtamodel/index.html
Hoping to get more documentation out in the coming weeks!
Trying to find time to develop tutorials.

## Slide 17: Other Significant TMG-Related Projects Undertaken
Modelling and Analysis of VfH Services in Support of City of Toronto Policy Analysis (City of Toronto Transportation Services):
  Supporting our PTC & Auto Passenger work.
Research and advisory support on transportation data collection and avoided emissions reporting (Housing, Infrastructure and Communities Canada):
  Developing the case for ABM transferability / standardization in Canadian cities.
TTC Economic Benefits Research Project, Phase 2 (TTC):
  Applying GTAModel to transit investment benefits analysis.
  Working at the service planning, rather than strategic planning level.

## Slide 18: Potential New Members
Monterrey, Mexico (Tecnólogico de Monterrey).
  Hopefully this year.
Region of Waterloo.
  Promising preliminary talks underway.
  Possibility of adopting GTAModel now that V4.3 will include Waterloo.

## Slide 19: Preliminary Look-Ahead
V5.0 / TASHA/2: Will be the primary focus.
As usual, will work with TMGTAC over the next several months to develop the draft 2026-27 workplan.

## Slide 20: Draft Budget
No change in individual contributions in 2026-27 from 2025-26.
Does not assume any new members or change in staff.

## Slide 21: Other Business

## Slide 22: Next Meeting
Wednesday, March 4, 2025
10:00-12:00
Online, Microsoft Teams
As usual, this meeting will deal with approval of the TMG 2026-27 workplan and budget.
We will also be celebrating 15 years of TMG operations!

## Slide 23: We are adjourned! Thank you!
The End!